## Project check list
STT | Features | Screen | Component | Sub Component | Task | Assignee | Detail | Pull Request (Link Github) | Estimated Hour (h) | Actual Hour (h) | Start Date | Finish Date | Sprint | Phase | Memo
1 | Home | Home page | Header | Navigator Left | Create UI | Toàn | Use an image to create Logo includding Url tag |  | 1 | 1 | 2021-03-07 | 2021-03-08 | 1 | 1
2 |  |  |  |  | Create function logic | toàn |  |  | 1 | 1 | 2021-03-07 | 2021-03-08 | 1 | 1
3 |  |  |  | Navigator Right | Create UI |  | There are 6 items inside menu which include HomePage,Cart,About,Contact,Products and Login/Register |  | 2 | 2 | 2021-03-07 | 2021-03-08 | 1 | 1
4 |  |  |  |  | Create function logic |  |  |  | 2 | 2 | 2021-03-07 | 2021-03-08 | 1 | 1 |  |  | 1 sprint: thường kéo dài khoảng 1-2 tuần
5 | [16 empty] | 1 phase thường khoản 4 dến 8 sprint
6 |  |  | Body | search product bar | Create UI | Toàn | Use an input element to create search bar |  | 1 | 1 | 2021-09-03 | 2021-09-03 | 1 | 1
7 |  |  |  |  | Create function logic | Toàn | Customers can search by name |  | 2 | 3 | 2021-09-03 | 2021-09-03 | 1 | 1
8 |  |  |  | Sort Products by Category,Size,Prices | Create UI |  | Use an input with type includes select options to create sort |  | 1 | 1 | 2021-09-03 | 2021-12-03 | 1 | 1 |  | Phase | Sprint | Start Date | Finish Date
9 |  |  |  |  | Create function logic | Toàn | User can sort products by category,order,size |  | 3 | 3.5 | 2021-09-03 | 2021-12-03 | 1 | 1 |  | 1 | 1 | 2021-03-07 | 2021-09-03
10 |  |  |  | Products List Container | Create UI | Toàn | Use div to wrap all products |  | 1 | 1 | 2021-09-03 | 2021-12-03 | 2 | 1 |  |  | 2 | 2021-09-03 | 18/03/2021
11 |  |  |  |  | Create function logic | Toàn |  |  | 2 | 2 | 2021-09-03 | 2021-12-03 | 2 | 1 |  |  | 3 | 18/03/2021 | 25/03/2021
12 |  |  |  | Panigation | Create UI | Toàn |  |  | 1 | 1 | 2021-09-03 | 2021-12-03 | 2 | 1 |  |  | 4 | 25/03/2021 | 29/03/2021
13 |  |  |  |  | Create function logic | Toàn | Use library React-Panigate to create panigation |  | 2 | 2 | 2021-09-03 | 2021-12-03 | 2 | 1
14 |  | Product Details Page | Product Desc | Info | Create UI | Toàn |  |  | 1 | 1.5 | 2021-12-03 | 18/03/2021 | 2 | 1
15 |  |  |  |  | Create function logic | Toàn |  |  | 1 | 1 | 2021-12-03 | 18/03/2021 | 2 | 1
|  |  |  | Details | Create UI | Toàn | Show all infomation about the product which customer chose |  | 2 | 2.5 | 2021-12-03 | 18/03/2021 | 2 | 1
[5 empty] | Create function logic | Toàn |  |  | 1 | 1 | 2021-12-03 | 18/03/2021 | 2 | 1
|  |  |  | Price | Create UI | Toàn | Show currently price and discount about product |  | 1 | 1 | 2021-12-03 | 18/03/2021 | 2 | 1
[5 empty] | Create function logic | Toàn |  |  | 1 | 1 | 2021-12-03 | 18/03/2021 | 2 | 1
|  |  |  | Add to cart | Create UI | Toàn |  |  | 1 | 1 | 2021-12-03 | 18/03/2021 | 2 | 1
[5 empty] | Create function logic | Toàn | Add to cart page |  | 2 | 3 | 2021-12-03 | 18/03/2021 | 2 | 1
| About | About page | About us | Info us | Create UI | Toàn |  |  | 1 | 1 | 20/03/2021 | 21/03/2021 | 3 | 1
[5 empty] | Create function logic | Toàn |  |  | 1 | 1 | 20/03/2021 | 21/03/2021 | 3 | 1
|  |  |  | Map | Create UI | Toàn |  |  | 1 | 2 | 20/03/2021 | 21/03/2021 | 3 | 1
[5 empty] | Create function logic | Toàn |  |  | 1 | 2 | 20/03/2021 | 21/03/2021 | 3 | 1
|  |  | About Website | Overview Introduction | Create UI | Toàn |  |  | 1 | 2 | 20/03/2021 | 21/03/2021 | 3 | 1
| Cart | Cart page | Cart items | Info Products | Create UI | Toàn | Info Products from Products or Homepage after customers chose includes name,price,discount,total |  | 1 | 2 | 21/03/2021 | 22/03/2021 | 3 | 1
[5 empty] | Create function logic | Toàn |  |  | 2 | 3 | 21/03/2021 | 22/03/2021 | 3 | 1
|  |  |  | cart methods | Create UI | Toàn | Includes increase , decrease and delete products |  | 1 | 2 | 22/03/2021 | 25/03/2021 | 3 | 1
[5 empty] | Create function logic | Toàn |  |  | 3 | 3.5 | 22/03/2021 | 25/03/2021 | 3 | 1
|  |  |  | Proceed order + Clear all order | Create UI | Toàn |  |  | 1 | 1 | 22/03/2021 | 25/03/2021 | 3 | 1
[5 empty] | Create function logic | Toàn |  |  | 2 | 3 | 22/03/2021 | 25/03/2021 | 3 | 1
| Contact | Contact Page | Contact our website | Form submit contact | Create UI | Toàn | Customers can give admin their contact or experiences after buying at shop |  | 1 | 2 | 25/03/2021 | 26/03/2021 | 4 | 1
[5 empty] | Create function logic | Toàn |  |  | 1 | 2 | 25/03/2021 | 26/03/2021 | 4 | 1
| Admin Dasboard | Admin home page | Admin layout | Side bar | Create UI | Toàn | Create info role and function for admin |  | 1 | 2 | 27/03/2021 | 29/03/2021 | 4 | 1
[5 empty] | Create function logic | Toàn |  |  | 1 | 2 | 27/03/2021 | 29/03/2021 | 4 | 1
|  |  |  | View Admin | Create UI | Toàn | show all information about admin |  | 1 | 2 | 27/03/2021 | 29/03/2021 | 4 | 1
[5 empty] | Create function logic | Toàn |  |  | 1 | 2 | 27/03/2021 | 29/03/2021 | 4 | 1
|  | Manage product | CRUD product | Add product | Create UI | Đăng
[5 empty] | Create function logic | Đăng
|  |  |  | Edit product | Create UI | Đăng
[5 empty] | Create function logic | Đăng
|  |  |  | List product | Create UI | Đăng
[5 empty] | Create function logic | Đăng
|  |  |  | Delete product | Create UI | Đăng
[5 empty] | Create function logic | Đăng
|  | Manage contact | CRUD contact | Edit contact | Create UI | Đăng
[5 empty] | Create function logic | Đăng
|  |  |  | List contact | Create UI | Đăng
[5 empty] | Create function logic | Đăng
|  |  |  | Delete contact | Create UI | Đăng
[5 empty] | Create function logic | Đăng
|  | Manage orders | Manage orders | Edit orders | Create UI | Đăng
[5 empty] | Create function logic | Đăng
|  |  |  | Delete orders | Create UI | Đăng
[5 empty] | Create function logic | Đăng